## Slide 1: Risky Business: Real Options for Software Development
Todd Little
@toddelittle

## Slide 2: Risky Business
Risky Business

## Slide 3: About Todd
Executive roles as VP Product Development, Director of Software & Technology
@toddelittle
Notes: Director – company called IHS until a few days ago
Just merged – 9,000 – 15,000
Information & analytics company, verticals
Performance reviews 10 years – mistake
Stopped laughing – launch
3 years ago – working off and on

## Slide 4: Weather Forecasting: Hurricane Rita
Notes: What can we say about every one of these predictions? They are wrong. But the collective set of predictions is quite useful. Which is more important when predicting hurricanes – where it hits or when it hits? Ok, both are important, but where is much more important than when. If you are in Florida you don’t really care when it hits. But once you know it has a chance to hit Houston then it is very important to know when it might hit.

## Slide 5: The Cone of Uncertainty
We expect uncertainty and manage for it through iterations, anticipation, and adaptation.
Notes: Inspection and adaptation is the answer. Iterations help bring in new information

## Slide 6: Managing the Coming Storm Inside the Cyclone
When will we get the requirements?
All in good time, my little pretty, all in good time
But I guess it doesn't matter anyway
Doesn't anybody believe me?
You're a very bad man!
Just give me your estimates by this afternoon
No, we need something today!
I already promised the customer it will be out in 6 months
No, we need it sooner.
Not so fast! Not so fast! ... I'll have to give the matter a little thought. Go away and come back tomorrow
Ok then, it will take 2 years.
Team Unity
Project Kickoff
Notes: We look at a typical software project…..

## Slide 7: We’re not in Kansas Anymore
My! People come and go so quickly here!
I may not come out alive, but I'm goin' in there!
The Great and Powerful Oz has got matters well in hand.
"Hee hee hee ha ha! Going so soon? I wouldn't hear of it! Why, my little party's just beginning!
Developer Hero
Reorg
Testing

## Slide 8: Movies
78% of Films Lose Money
6% of films make 80% of profit
Notes: Most movies strive to be the next Titanic, the largest grossing film of all time.
The reality is that the vast majority really do end up closer to the real Titanic than to the movie Titanic.

## Slide 9: Books
300,000 in 2004,
<25% sold more
Than 100 copies
Notes: Books. Here is my book. Doesn’t it look like it is chock full of useful stuff?
But only 25% of books sell more than 100 copies. Please do your part so that I am not part of that statistic.

## Slide 10: Poker

## Slide 11: Poker Metric: Percent of Hands Won

## Slide 12: The Context of Feedback

## Slide 13: Oil & Gas Exploration
Notes: Oil exploration is highly risky. It used to be that 10% was a good find rate for wildcat wells. Based on improvements in technology this is closer to 20%. Still risky, but that risk is acceptable because the payout is enormous. The key is having a diversified portfolio to balance the risk exposure.

## Slide 14: Oil & Gas Exploration
90-80% Failure
Notes: Oil exploration is highly risky. It used to be that 10% was a good find rate for wildcat wells. Based on improvements in technology this is closer to 20%. Still risky, but that risk is acceptable because the payout is enormous. The key is having a diversified portfolio to balance the risk exposure.

## Slide 15
I’m beginning to think it wasn’t such a good idea to turn off those unit tests
Notes:   Safety is not to be messed with.
  Test, Test, Test
  Test again with real data
  Test, Test, Test
  Test again with real data

## Slide 16: Gordon the Guided Missile

## Slide 17: Risk management tools
Risk Management Tools

## Slide 18: Estimate the # of Jelly Beans

## Slide 19: Cynefin Framework (Snowden)

## Slide 20: Obvious
Input
Output
Cause and Effect Obvious to all
Known - Knowns
Sense - Categorize - Respond
apply best practice
Distribution
Example: Manufacturing

## Slide 21: Complicated
Input
Output
Cause and Effect Requires Analysis
Known - Unknowns
Sense - Analyze – Respond
apply good practice
Distribution
Example: Incremental Product Development
Analysis

## Slide 22: Complex
Input
Cause and Effect perceived in retrospect
Unknown - Unknowns
Probe - Sense – Respond
sense emergent practice
Distribution
Output
Example: New Product Development

## Slide 23: Chaotic
Input
Output
No Relationship between Cause and Effect
Unknowables
Act - Sense - Respond
discover novel practice.
Distribution
Example: Medical Emergency

## Slide 24: Control Systems
Processes
Inputs
Inputs
Inputs
Processes
Inputs
Inputs
Inputs
Command & Control
Agile Leadership
Outputs

## Slide 25: Lean startup

## Slide 26
Value of Information
Cost of Delay
Value of Uncertainty
Tornado Chart
Real Options
Value of Flexibility

## Slide 27: Real Options
The right — but not the obligation — to undertake certain actions prior to an expiry date

## Slide 28: Airline Tickets
The right — but not the obligation — to undertake certain actions prior to an expiry date

## Slide 29: Real Options

## Slide 30: Real Options
The right, but not the obligation to take some action prior to an expiry date

## Slide 31: Do you have a choice?
Option
Commitment
Decision

## Slide 32
Notes: http://www.flickr.com/photos/nick_anderson/5049751331/sizes/m/in/photostream/

## Slide 33: Which risks are important?
Notes: Which risks are important? The sharp edges of the sign or the fact that the bridge is out ahead?

## Slide 34: Tornado Chart: Which Uncertainties Are Important?
Notes: Oil and gas geologists and engineers build models to help them comprehend the uncertainties. This is a tornado chart, because it looks like a tornado. This chart clearly shows that the largest uncertainty is associated with Reserves, with the next largest uncertainty being oil/gas price. This gives the engineer something to focus on. Perhaps there is additional data that can be collected to help reduce the uncertainty bars. There may not be anything that can be done about Oil/gas price. Perhaps futures contracts could be used to hedge some of the uncertainty. The other uncertainties may not be worth spending too much time since they have limited effect on the total uncertainty.

## Slide 35: Value of Uncertainty
What is the source of all value?

## Slide 36: Eliminating Risk/Uncertainty is not the Goal!
Efficient Frontier

## Slide 37: Software Tornado Example
Item | -15M |  | 0M |  | 15M |  | 30M |  | 45M | 
Product Acceptance Uncertainty |  |  | ██ | ███ | ███ | ███ | ███ | ███ | ███ | 
Schedule Uncertainty |  |  | █ | ███ | ███ | ██ |  |  |  | 
General Market Uncertainty |  |  |  |  | ██ | ██ |  |  |  | 
Cost Uncertainty |  |  |  |  | ██ | █ |  |  |  | 

## Slide 38: Software Tornado Example
Item | -15M |  | 0M |  | 15M |  | 30M |  | 45M | 
Product Acceptance Uncertainty |  |  |  | ███ | ███ | ███ | ███ | ███ | ███ | 
Schedule Uncertainty |  |  |  | ███ | ███ | ██ |  |  |  | 
General Market Uncertainty |  |  |  |  | ██ | ██ |  |  |  | 
Cost Uncertainty |  |  |  |  | ██ | █ |  |  |  | 

## Slide 39: Software Tornado Example
Item | -15M |  | 0M |  | 15M |  | 30M |  | 45M | 
Product Acceptance Uncertainty |  |  |  | ███ | ███ |  |  |  |  | 
Schedule Uncertainty |  |  |  | ███ | ██ |  |  |  |  | 
General Market Uncertainty |  |  |  | ██ | ██ |  |  |  |  | 
Cost Uncertainty |  |  |  | ██ | █ |  |  |  |  | 

## Slide 40: Value of Information

## Slide 41: Value of Information

## Slide 42: Value of Information

## Slide 43: Value of Flexibility
Notes: 9 research projects for drive train
1 chassis – same hole for all 9 drive trains
VOI from 9 research projects, VOF from chassis design
Contrast this with the development of the Prius. Toyota had 9 different research projects running to develop hybrid engine technologies. Normally they would choose a drivetrain first, and build a car around it. Instead Toyota decided to keep its options open, and designed the Prius with a hole in it for the drive train. The 9 research projects continued, and 9+ months after the Prius development project was started, a drive train was chosen. Toyota knew that this car needed a radically new drive train architecture. Instead of guessing and choosing one, they let all 9 research projects continue their work, and as they did, the best option for the car's engine became clear. So was 9 research projects a waste? No because each project was generating factual information about the options for hybrid engine design, information that Toyota engineering management needed to make an informed choice.

## Slide 44: Value of Flexibility from Loose Coupling

## Slide 46: Cost of Delay
Value Loss from Delay

## Slide 47: Wrong Priorities?
Notes: The first generation of Ford Taurus turned out to be the best selling car in America in the
late 1980s. Conceived in the 1980's and introduced in 1986, it set the standard for new practices
in project management and product development. It was one of the early projects in the U.S.,
which fully utilized the concept of cross-functional teams and concurrent engineering practices.
It established close ties with vendors and subcontractors, and was characterized by a spirit of
cooperation and strong synergy among teams. The result was a remarkable market and business
success. Its revolutionary design and outstanding quality, created a new trend in the U.S.
automobile industry, and customers simply loved the car. Yet, when the project was completed,
the project manager was fired. His “sin” was that project completion was delayed by six months.
In contrast, the second generation of Ford Taurus was developed in the early 1990s and
2
completed in 1995. With increased competition and the enormous success of Japanese imports,
Ford had hoped to reestablish Taurus, once again, as the best selling car in America. But the new
project manager learned the lesson of his predecessor: He considered project schedule as a “holy
grail,” and made sticking to the completion date the ultimate goal, while sacrificing other things.
Vendor relationships, team spirit, and product integration were just few of the issues that
suffered. The second generation of Taurus turned out to be a disappointing business experience.
It did not recapture the position of the best selling car in America and Ford was not able to repeat
its outstanding success of the first Taurus.

## Slide 48: The Measurement Inversion
Lowest
Information Value
Highest Information Value
Most Measured
Least Measured
Cost & Time
Value Delivery

## Slide 49: Risk Management is NOT Risk Aversion

## Slide 50: Contact
Todd Little
  toddelittle@gmail.com
  www.linkedin.com/in/toddelittle/
  @toddelittle
  www.toddlittleweb.com
  www.accelinnova.com

## Slide 51: Jellybean Results
Type of Estimate | Typical Ranges
Individual Estimates | 0.30 – 1.8 (6X)
Groups (of ~6) | 0.75 – 1.50 (2X)
Average of the Individuals | 0.80 – 1.20

## Slide 52: Actual vs. Original Estimate
Chart: 
| 10-20% | 50% | 80-90%
Series 1 | 1 | 2 | 4
P90/P10 = 4