## Slide 1: Exploring Little’s Law
Todd Little
Chairman Kanban University
Lead Time
(Time in System)
Work In Progress
(Number of Customers)
Throughput
(Arrival/Departure Rate)

## Slide 2: Estimate the # of Jelly Beans
Rules
Quiet
No collaboration
Just a Number
Name
Number

## Slide 3: Exploring Little’s Law
Todd Little
Chairman Kanban University
Lead Time
(Time in System)
Work In Progress
(Number of Customers)
Throughput
(Arrival/Departure Rate)

## Slide 4: Little’s LλW (John D. C. Little version)
“The average number of customers in a system (over some interval) is equal to their average arrival rate, multiplied by their average time in the system."
    L = λW
Average Length of Queue
Average Arrival Rate
Average Wait Time

## Slide 5: Little’s Law in Knowledge Work
Lead Time
(Time in System)
Work In Progress
(Number of Customers)
Throughput
(Arrival/Departure Rate)
Little’s Law Assumptions – The System is Stable and running at capacity
The average Arrival Rate is equal to the average Departure Rate
Stable system
WIP increasing
WIP decreasing
Cumulative Flow Diagrams

## Slide 6: Little’s Law in Action

## Slide 7: Flow Efficiency, Utilization, and Capacity
Traveling time largely determined by delays.
Few delays
Notes: Focus the discussion on the time you’ll need through the system.
The cars in the left picture experience no to little delay in their travel, the cars on the right have a lot of delays on their way. Their “lead time” (time to pass the system = the part of the road) is determined largely by the waiting time, not by the time they actually drive.
Therefore, travelling on the left side is preferable, as less time is spent to cover the same mileage.
How does your Kanban Board / your project portfolio look like, and why?
Traditional management paradigms often focus on utilization (using the space available on the highway) rather than flow (getting cars quickly and smoothly through the system).

## Slide 8: Summary of Video Results
WIP | Lead Time | Throughput | Flow Efficiency | Utilization
1 | 90 | 0.11 | 1.00 | 0.44
2 | 90 | 0.22 | 1.00 | 0.89
3 | 120 | 0.25 | 0.75 | 1.00
4 | 160 | 0.25 | 0.56 | 1.00
5 | 200 | 0.25 | 0.45 | 1.00

## Slide 9: Flow Efficiency, Efficiency, Lead Time and Throughput
Chart: Little's Law
| 1 | 2 | 3 | 4 | 5
Throughput | 0.11111 | 0.22222 | 0.25 | 0.25 | 0.25
Flow Efficiency | 1 | 1 | 0.75 | 0.5625 | 0.45
Efficiency | 0.44444 | 0.88889 | 1 | 1 | 1
Lead Time | 90 | 90 | 120 | 160 | 200

## Slide 10: What does Little’s Law say about Overburdening?

## Slide 11: Design for Flow

## Slide 12: Be Like Water - Continuity Equation
10x1
5x2
5x1
Q = 10 m3/sec A = 10 m2 v = 1 m/sec
Q = 10 m3/sec A = 10 m2
v = 1 m/sec
Q = 10 m3/sec A = 5 m2 v = 2 m/sec
Q = A * v

## Slide 13: Be Like Water – College Chem E Version Input – Output = Accumulation
Input
Ouput
Process
Accumulation

## Slide 14: Smooth Flow Throughout Optimize the Bottleneck

## Slide 15
Kanban System Design for XIT
User Acceptance
Test
Lead time of ? days or less
Development
Testing
WIP = ?
WIP = ?
Commitment Point
WIP = ?
WIP = ?
WIP = ?
Backlog of
Options
Change
Requests
PTC
Expedite
PM
Product
Managers
Notes: Here is the complete kanban system design for XIT. Note that there is a lead time expectation expressed as 30 days or less. (This slide appears multiple times as a reminder.)

## Slide 16
Kanban System Design for XIT
User Acceptance
Test
Development
Testing
WIP = ?
WIP = ?
Commitment Point
WIP = ?
WIP = ?
WIP = ?
Backlog of
Options
Change
Requests
PTC
Expedite
PM
Product
Managers
System Lead Time
Dev Time
Cycle Time
Lead time of ? days or less
Notes: Here is the complete kanban system design for XIT. Note that there is a lead time expectation expressed as 30 days or less. (This slide appears multiple times as a reminder.)

## Slide 17: Design Rules
Start with what data you have. It need not be perfect
Design for the bottleneck
  For XIT - Engineering and Test
Throughput is constant through the flow
Queues – large enough to prevent starvation, small enough to keep lead time small
Difference between WIP Limit and Average WIP

## Slide 18: Let’s get started

## Slide 19: Little’s LλW (John D. C. Little version)
Not Little’s Law, but sometimes useful

## Slide 20: Little’s Law @XIT
 | System |  | Ready | Dev | Dev Done | Test | UAT
Ave Throughput |  |  |  |  |  |  | 
WIP Average |  |  |  |  |  |  | 
Ave Lead Time |  |  |  |  |  |  | 
WIP Limit |  |  |  |  |  |  | 
Max Lead Time |  |  |  |  |  |  | 

## Slide 21: Determining an Expectation of Service Delivery
Engineering effort (touch time)
  Average engineering time was 11 days with outliers > 24 days
Demand rate is 10-12 CR per month – can we meet it?
Throughput
Lead Time
Work In Progress
Notes: The XIT group determined their current engineering delivery rate and the expectation (hypothesis) of the engineering delivery rate if they removed estimation.

## Slide 22: Little’s Law @XIT
 | System |  | Ready | Dev | Dev Done | Test | UAT
Ave Throughput |  |  |  |  |  |  | 
WIP Average |  |  |  | 3 |  | 3 | 
Ave Lead Time |  |  |  | 5.5 |  | 5.5 | 
WIP Limit |  |  |  | 3 |  | 3 | 
Max Lead Time |  |  |  | 12 |  | 12 | 

## Slide 23: Determining an Expectation of Service Delivery
Engineering effort (touch time)
  Average engineering time was 11 days with outliers > 24 days
Demand rate is 10-12 CR per month – can we meet it?
Delivery rate estimate
  Without estimation interruptions or multitasking, we have:
    WIP = 6 (3 dev + 3 test)
    Average Lead Time = 11 days
    0.55 items/day 11 items/mo
Queuing & buffering time estimates
  Queues: large enough to prevent starvation, small enough to keep Lead Time small.
Throughput
Lead Time
Work In Progress
Notes: The XIT group determined their current engineering delivery rate and the expectation (hypothesis) of the engineering delivery rate if they removed estimation.

## Slide 24: Little’s Law @XIT
 | System |  | Ready | Dev | Dev Done | Test | UAT
Ave Throughput |  |  |  | 0.55 |  | 0.55 | 
WIP Average |  |  |  | 3 |  | 3 | 
Ave Lead Time |  |  |  | 5.5 |  | 5.5 | 
WIP Limit |  |  |  | 3 |  | 3 | 
Max Lead Time |  |  |  | 12 |  | 12 | 

## Slide 25: Be Like Water – College Chem E Version Input – Output = Accumulation
Input
Ouput
Process
Accumulation

## Slide 26: Little’s Law @XIT - Smooth flow throughout
 | System |  | Ready | Dev | Dev Done | Test | UAT
Ave Throughput | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55
WIP Average |  |  |  | 3 |  | 3 | 
Ave Lead Time |  |  |  | 5.5 |  | 5.5 | 
WIP Limit |  |  |  | 3 |  | 3 | 
Max Lead Time |  |  |  | 12 |  | 12 | 

## Slide 27: Queues and WIP limits
Ready Queue
  Replenishment will be weekly.
  Allow 2X buffer to prevent starvation
  What is Starting WIP, Ending WIP, Average WIP?
  Average Throughput of 2.7 items/week ( 5 x 0.55 )
  Start with WIP limit of 5 to allow 2x buffer
  Beginning WIP of 5, Ending Average WIP of 5-2.7=2.3
  Average WIP of 5-(5-2.7)/2 = 3.65

## Slide 28: Little’s Law @XIT - Replenishment
 | System |  | Ready | Dev | Dev Done | Test | UAT
Ave Throughput | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55
WIP Average |  |  | 3.65 | 3 |  | 3 | 
Ave Lead Time |  |  | 6.6 | 5.5 |  | 5.5 | 
WIP Limit |  |  | 5 | 3 |  | 3 | 
Max Lead Time |  |  | 10 | 12 |  | 12 | 

## Slide 29: Queues and WIP limits
Dev Done Queue
  3 items will be in Test with average Lead Time of 6 days.
  How frequent does a Test slot free up?
  On average, Test will free one slot every 2 days
  Assume average Lead Time of 2 in Dev Done Queue

## Slide 30: Little’s Law @XIT - Dev Done Buffer
 | System |  | Ready | Dev | Dev Done | Test | UAT
Ave Throughput | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55
WIP Average |  |  | 3.65 | 3 | 1.1 | 3 | 
Ave Lead Time |  |  | 6.6 | 5.5 | 2 | 5.5 | 
WIP Limit |  |  | 5 | 3 | 2 | 3 | 
Max Lead Time |  |  | 10 | 12 | 3.6 | 12 | 

## Slide 31: Queues and WIP limits
UAT
  Max Lead Time of 10 days.
  WIP Limit of 10 * 0.55 = 5.5 – round up to 6
  Assume Average WIP of ½ limit = 3

## Slide 32: Little’s Law @XIT - UAT Buffer
 | System |  | Ready | Dev | Dev Done | Test | UAT
Ave Throughput | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55
WIP Average |  |  | 3.65 | 3 | 1.1 | 3 | 3
Ave Lead Time |  |  | 6.6 | 5.5 | 2 | 5.5 | 5.5
WIP Limit |  |  | 5 | 3 | 2 | 3 | 6
Max Lead Time |  |  | 10 | 12 | 3.6 | 12 | 10

## Slide 33: Little’s Law @XIT - System
 | System |  | Ready | Dev | Dev Done | Test | UAT
Ave Throughput | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55
WIP Average | 13.7 |  | 3.65 | 3 | 1.1 | 3 | 3
Ave Lead Time | 25.1 |  | 6.6 | 5.5 | 2 | 5.5 | 5.5
WIP Limit | 19 |  | 5 | 3 | 2 | 3 | 6
Max Lead Time | 47.6 |  | 10 | 12 | 3.6 | 12 | 10

## Slide 34
 | System |  | Ready | Dev | Dev Done | Test | UAT
Ave Throughput | 0.55 |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55
WIP Average | 13.7 |  | 3.65 | 3 | 1.1 | 3 | 3
Ave Lead Time | 25.1 |  | 6.6 | 5.5 | 2 | 5.5 | 5.5
WIP Limit | 19 |  | 5 | 3 | 2 | 3 | 6
Max Lead Time | 47.6 |  | 10 | 12 | 3.6 | 12 | 10
Can we meet a target Lead Time of 30 days with a high (98%) Service Expectation?
What knobs might you tweak to help meet the SLE?

## Slide 35
Kanban System Design for XIT
User Acceptance
Test
Lead time of 30 days or less
Development
Testing
WIP = 3
WIP = 3
Commitment Point
WIP = 5
WIP = 5
WIP = 6
Backlog of
Options
Change
Requests
PTC
Expedite
PM
Product
Managers
System will stall in approximately
2 weeks if not serviced
Notes: Here is the complete kanban system design for XIT. Note that there is a lead time expectation expressed as 30 days or less. (This slide appears multiple times as a reminder.)

## Slide 36: Forecasting with Little’s Law

## Slide 37: Let’s play a game

## Slide 38: Google Spreadsheet
bit.ly/3PGymF9
Little's Law Tally Sheet |  |  |  |  |  |  | 
Y(cards) |  |  |  | X | Y(points) | =Cum Actual (E)*132 / Cum Size (F) | =Cum Actual (E) *20 / # Cards (A)
Card | Size | Die roll | Actual Time | Cummulative Actual | Cummulative Size | Size Forecast | Count Forecast
1 |  |  |  |  |  |  | 
2 |  |  |  |  |  |  | 
3 |  |  |  |  |  |  | 
4 |  |  |  |  |  |  | 
5 |  |  |  |  |  |  | 
6 |  |  |  |  |  |  | 
7 |  |  |  |  |  |  | 
8 |  |  |  |  |  |  | 
9 |  |  |  |  |  |  | 
10 |  |  |  |  |  |  | 
11 |  |  |  |  |  |  | 
12 |  |  |  |  |  |  | 
13 |  |  |  |  |  |  | 
14 |  |  |  |  |  |  | 
15 |  |  |  |  |  |  | 
16 |  |  |  |  |  |  | 
17 |  |  |  |  |  |  | 
18 |  |  |  |  |  |  | 
19 |  |  |  |  |  |  | 
20 |  |  |  |  |  |  | 
Old School

## Slide 39: Serious Old School
Chart: Points vs Time
| 0 | 250
Points | 0 | 132
 | 132 | 132
Chart: Cards vs. Time
| 0 | 250
Cards | 0 | 20
Little's Law Tally Sheet |  |  |  |  |  |  | 
Y(cards) |  |  |  | X | Y(points) | =Cum Actual (E)*132 / Cum Size (F) | =Cum Actual (E) *20 / # Cards (A)
Card | Size | Die roll | Actual Time | Cummulative Actual | Cummulative Size | Size Forecast | Count Forecast
1 |  |  |  |  |  |  | 
2 |  |  |  |  |  |  | 
3 |  |  |  |  |  |  | 
4 |  |  |  |  |  |  | 
5 |  |  |  |  |  |  | 
6 |  |  |  |  |  |  | 
7 |  |  |  |  |  |  | 
8 |  |  |  |  |  |  | 
9 |  |  |  |  |  |  | 
10 |  |  |  |  |  |  | 
11 |  |  |  |  |  |  | 
12 |  |  |  |  |  |  | 
13 |  |  |  |  |  |  | 
14 |  |  |  |  |  |  | 
15 |  |  |  |  |  |  | 
16 |  |  |  |  |  |  | 
17 |  |  |  |  |  |  | 
18 |  |  |  |  |  |  | 
19 |  |  |  |  |  |  | 
20 |  |  |  |  |  |  | 

## Slide 40: Per Table
Adjustment Table |  |  |  |  |  | 
 | Card Value |  |  |  |  | 
Die | 2 | 3 | 5 | 8 | 13 | 20
1 | 1 | 2 | 3 | 4 | 8 | 13
2 | 1 | 2 | 4 | 6 | 10 | 16
3 | 2 | 3 | 5 | 8 | 13 | 20
4 | 2 | 3 | 5 | 8 | 13 | 20
5 | 4 | 6 | 7 | 11 | 16 | 25
6 | 6 | 8 | 10 | 16 | 22 | 30
Deck of Cards

## Slide 41: Per person
Chart: Points vs Time
| 0 | 250
Points | 0 | 132
 | 132 | 132
Chart: Cards vs. Time
| 0 | 250
Cards | 0 | 20
Little's Law Tally Sheet |  |  |  |  |  |  | 
Y(cards) |  |  |  | X | Y(points) | =Cum Actual (E)*132 / Cum Size (F) | =Cum Actual (E) *20 / # Cards (A)
Card | Size | Die roll | Actual Time | Cummulative Actual | Cummulative Size | Size Forecast | Count Forecast
1 |  |  |  |  |  |  | 
2 |  |  |  |  |  |  | 
3 |  |  |  |  |  |  | 
4 |  |  |  |  |  |  | 
5 |  |  |  |  |  |  | 
6 |  |  |  |  |  |  | 
7 |  |  |  |  |  |  | 
8 |  |  |  |  |  |  | 
9 |  |  |  |  |  |  | 
10 |  |  |  |  |  |  | 
11 |  |  |  |  |  |  | 
12 |  |  |  |  |  |  | 
13 |  |  |  |  |  |  | 
14 |  |  |  |  |  |  | 
15 |  |  |  |  |  |  | 
16 |  |  |  |  |  |  | 
17 |  |  |  |  |  |  | 
18 |  |  |  |  |  |  | 
19 |  |  |  |  |  |  | 
20 |  |  |  |  |  |  | 

## Slide 42: Background
Each card represents a story in the backlog.
They have been estimated through rigorous Planning Poker
We will process cards sequentially,
but each table will have a different order
Please shuffle the deck of cards (but not after each draw)
Cards will then be pulled sequentially
Each person will implement the story by rolling their die
The die will tell us how accurate the estimate was and how long it really takes

## Slide 43: Example: Draw a card to be used by everyone at the table
13
Now each person rolls their die

## Slide 44
Adjustment Table |  |  |  |  |  | 
 | Card Value |  |  |  |  | 
Die | 2 | 3 | 5 | 8 | 13 | 20
1 | 1 | 2 | 3 | 4 | 8 | 13
2 | 1 | 2 | 4 | 6 | 10 | 16
3 | 2 | 3 | 5 | 8 | 13 | 20
4 | 2 | 3 | 5 | 8 | 13 | 20
5 | 4 | 6 | 7 | 11 | 16 | 25
6 | 6 | 8 | 10 | 16 | 22 | 30

## Slide 45
Little's Law Tally Sheet |  |  |  |  |  |  | 
Y(cards) |  |  |  | X | Y(points) | =Cum Actual (E)*132 / Cum Size (F) | =Cum Actual (E) *20 / # Cards (A)
Card | Size | Die roll | Actual Time | Cummulative Actual | Cummulative Size | Size Forecast | Count Forecast
1 | 13 | 5 | 16 | 16 | 13 |  | 
2 |  |  |  |  |  |  | 
3 |  |  |  |  |  |  | 
4 |  |  |  |  |  |  | 
5 |  |  |  |  |  |  | 
6 |  |  |  |  |  |  | 
7 |  |  |  |  |  |  | 
8 |  |  |  |  |  |  | 
9 |  |  |  |  |  |  | 
10 |  |  |  |  |  |  | 
Card
Die
Lookup
Sum Actual
Sum Size

## Slide 46
Chart: Points vs Time
| 0 | 250
Points | 0 | 132
 | 132 | 132

## Slide 47
Chart: Cards vs. Time
| 0 | 250
Cards | 0 | 20

## Slide 48: Google Spreadsheet
bit.ly/3PGymF9
Little's Law Tally Sheet |  |  |  |  |  |  | 
Y(cards) |  |  |  | X | Y(points) | =Cum Actual (E)*132 / Cum Size (F) | =Cum Actual (E) *20 / # Cards (A)
Card | Size | Die roll | Actual Time | Cummulative Actual | Cummulative Size | Size Forecast | Count Forecast
1 |  |  |  |  |  |  | 
2 |  |  |  |  |  |  | 
3 |  |  |  |  |  |  | 
4 |  |  |  |  |  |  | 
5 |  |  |  |  |  |  | 
6 |  |  |  |  |  |  | 
7 |  |  |  |  |  |  | 
8 |  |  |  |  |  |  | 
9 |  |  |  |  |  |  | 
10 |  |  |  |  |  |  | 
11 |  |  |  |  |  |  | 
12 |  |  |  |  |  |  | 
13 |  |  |  |  |  |  | 
14 |  |  |  |  |  |  | 
15 |  |  |  |  |  |  | 
16 |  |  |  |  |  |  | 
17 |  |  |  |  |  |  | 
18 |  |  |  |  |  |  | 
19 |  |  |  |  |  |  | 
20 |  |  |  |  |  |  | 
Old School

## Slide 49: Let’s do 1 card Draw a card to be used by everyone at the table
?
Now each person rolls their die

## Slide 50: Task switching – Sometimes batches are better
Run through 5 cards recording on the Tally Sheet
Calculate the Forecast based on the trends of the first 5 cards
  Size Forecast = Cum Actual (E)*132 / Cum Size (F)
  Count Forecast = Cum Actual (E) *20 / # Cards (A)
Continue with the remaining 15 cards in batches of 5
Old School – plot away

## Slide 51: Forecasting
132 total points in 20 total cards
Forecast (size) = Cumulative Actual * 132/ Cumulative Size
Cumulative Actual
Cumulative Size
132
Cumulative Actual
Forecast (card) = Cumulative Actual * 20/ # Cards
20
# Cards

## Slide 52
Little's Law Tally Sheet |  |  |  |  |  |  | 
Y(cards) |  |  |  | X | Y(points) | =Cum Actual (E)*132 / Cum Size (F) | =Cum Actual (E) *20 / # Cards (A)
Card | Size | Die roll | Actual Time | Cumulative Actual | Cumulative Size | Size Forecast | Count Forecast
1 | 13 | 5 | 16 | 16 | 13 |  | 
2 | 5 | 3 | 5 | 21 | 18 |  | 
3 | 8 | 2 | 6 | 27 | 26 |  | 
4 | 2 | 6 | 6 | 33 | 28 |  | 
5 | 5 | 1 | 3 | 36 | 33 | 144 | 144
6 |  |  |  |  |  |  | 
7 |  |  |  |  |  |  | 
8 |  |  |  |  |  |  | 
9 |  |  |  |  |  |  | 
10 |  |  |  |  |  |  | 

## Slide 53: Final Summary
Card | Size | Die roll | Actual Time | Cumulative Actual | Cumulative Size | Size Forecast | Count Forecast
5 |  |  |  |  |  |  | 
10 |  |  |  |  |  |  | 
15 |  |  |  |  |  |  | 
20 |  |  |  |  |  |  | 

## Slide 54: Monte Carlo Simulation Results

## Slide 55: Data needs to be Thin-tailed for Little’s Law
P90/P10 <20

## Slide 56: Estimate the # of Jelly Beans